## Sheet1
Seq | Code | Stream | CASE ID | Testing Type | Effected YN | Effected by Change | System | Test Name | Test Description | Pre-requisites / Assumptions | Expected Outcome | Testers | Busness Owner | Testing Teams | Pass/Fail | PERSONA | SUPPLIER | BMO OU (LENC) | SUBSIDIARY | PAYGROUP | Other Test Data | Downstream App Validation | Oracle OIT | Oracle TAX validation | FA Validation | Artifact Ref. | Comments
100 | Story 1 | Sourcing project and event management lifecycle | Story 1-100 | End to End UAT User Stories |  |  | SmartSource |  | A BOTW user submits a new Sourcing Intake for procuring a new product/service. A new Sourcing project is created, and an event is launched to non-incumbent suppliers with expected multi-year savings.
101 | Story 2 | SEMS Risk Assessment Supplier Enablement and Setup Processes | Story 2-101 | End to End UAT User Stories |  |  | CRA (SEMS) SmartProcure Oracle |  | A new supplier from the US west coast is being assessed for IR. This supplier will cater services to BMO Bank NA. Based on risk assessment, a shell supplier record (servicing BMO Bank NA) is created in the supplier master. The shell record of the supplier is enriched for purchasing enablement based on award
102 | Story 3 | Contract Lifecycle Management Processes | Story 3-102 | End to End UAT User Stories |  |  | CLM |  | A new master agreement (MSA) is being signed with a new supplier under the BMO Bank NA legal entity. An Order is being executed under the newly signed MSA adding details on scope of services and associated costs.
103 | Story 4 | Contract Lifecycle Management Processes | Story 4-103 | End to End UAT User Stories |  |  | CLM |  | An existing BMO Harris MSA is being amendment to restate some BOTW synergy related work services
104 | Story 5 | Purchasing Lifecycle AP Processing Lifecycle | Story 5-104 | End to End UAT User Stories |  |  | SmartProcure Oracle |  | A BOTW user creates a requisition on BMO SmartProcure (BSP) to purchase office supplies from the standard catalogue built into BSP. The requisition is then approved based on the approval limits associated to the cart value. Once the requisition is approved, a purchase order is issued to the supplier for fulfilment. Upon completion, the supplier issues an invoice to BSP which follows the standard AP protocols for accounting and payment. Once fully approved in Oracle, the payment is issued to the supplier based on the payment terms. The fully paid confirmation is sent bask to BSP and accounting entries are sent to BMO Bank NA GL systems.
105 | Story 6 | Purchasing Lifecycle AP Processing Lifecycle FA Processing Lifecycle | Story 6-105 | End to End UAT User Stories |  |  | SmartProcure Oracle |  | A BOTW user creates a requisition on BSP to purchase a server (FA commodity). The requisition then flows to invoice payment based the standard purchasing policies and goes through the standard AP accounting and payment processes. Since this is a Fixed Asset commodity, the asset is processed through the mass addition, capitalization, depreciation steps by the Fixed Asset team. Upon accounting period close, the assets are booked into the BMO Bank NA GL systems.
106 | Story 7 | Trusted Systems, Punch-Outs / Punch-Through, CSV Integration | Story 7-106 | End to End UAT User Stories |  |  | SmartProcure Oracle |  | A purchase was made via a punch-out solution which created a requisition back in the BSP system. The supplier then invoiced via integration which was processed through the standard purchasing and AP processes.
107 | Story 8 | Trusted Systems, Punch-Outs / Punch-Through, CSV Integration | Story 8-107 | End to End UAT User Stories |  |  | SmartProcure Oracle |  | A purchase was made via punch-through solution where the purchase order was raised directly in the external system. The supplier then invoiced via integration which was processed through the standard purchasing and AP processes
108 | Story 9 | AP Processing Lifecycle | Story 9-108 | End to End UAT User Stories |  |  | SmartProcure Oracle |  | A payment batch is issued on the BMO Bank NA pay group
109 | Story 10 | AP Processing Lifecycle Corporate cards and Expense processes | Story 10-109 | End to End UAT User Stories |  |  | SmartProcure Oracle |  | A payment is issued to a BOTW employee for out-of-pocket expense reimbursement
110 | Story 11 | AP period-closing processes including reconciliation, accounting and feeds to GL systems | Story 11-110 | End to End UAT User Stories |  |  | SmartProcure Oracle |  | AP period-closing processes including reconciliation, accounting and feeds to GL systems
111 | Story 12 | AP Processing Lifecycle Corporate cards and Expense processes | Story 12-111 | End to End UAT User Stories |  |  | SmartProcure Oracle |  | A BOTW user makes an out-of-pocket expense using their personal card and creates an expense report for processing and payment to payroll bank account
112 | Story 13 | AP Processing Lifecycle Corporate cards and Expense processes | Story 13-112 | End to End UAT User Stories |  |  | SmartProcure Oracle |  | A BOTW user charges an expense item via the corporate card and creates an expense report for processing and payment for Mastercard
113 | Story 14 | Lease Admin Processes AP Processing Lifecycle | Story 14-113 | End to End UAT User Stories |  |  | Horizon Oracle SmartProcure |  | A new BOTW lease agreement has been signed that needs to onboarded through the lease administration program. This lease is managed through its validity and a periodic rent payment file is issued for payment.
114 | Story 15 | External Labour Hiring Lifecycle AP Processing Lifecycle | Story 15-114 | End to End UAT User Stories |  |  | SmartProcure Oracle Beeline |  | BOTW needs to hire a contractor under the Staff Augmentation program for which timesheet management is conducted in Beeline. Once the timesheets are approved, the subsequent PO and invoices are fed through to BSP for payments processing
115 | Story 16 | External Labour Hiring Lifecycle AP Processing Lifecycle | Story 16-115 | End to End UAT User Stories |  |  | SmartProcure Oracle Beeline |  | BOTW needs to hire a contractor under the Staff Augmentation program for which timesheet management is conducted in Clarity. Once the timesheets are approved in Clarity, the timesheet is brought back into Beeline which then subsequently releases the PO and invoices feed to BSP for payments processing.
116 | CRA | SEMS risk assessment processes | CRA-116 | Functionality | YES | LENC, Retrofit | SEMS | SEPARATE TESTING for LENC |  |  |  | Brandon | Jessica Klein | GTPRM | TO TEST
117 | CRA | SEMS risk assessment processes | CRA-117 | E2E | YES | LENC, Retrofit | SEMS | SEPARATE TESTING for LENC |  |  |  | Brandon | Jessica Klein | GTPRM | TO TEST
118 | TRIAGE | Sourcing project and event management lifecycle | TRIAGE-118 | Functionality | YES | LENC | SEMS, Coupa | Creating Sourcing Projects |  |  |  | Jacob DeLaurentis | Dan Muldoon | Triage | TO TEST
119 | SSM | Sourcing project and event management lifecycle | SSM-119 | Functionality |  | BAU | SmartSource | Ability to edit Sourcing Projects | Edit project, update status and leave a comment |  | Status change and comment left. History section to capture changes made | Mark Silvestrin | Jason Ungeran | Sourcing | TO TEST |  |  | BMO Harris N.A.
120 | SSM | Sourcing project and event management lifecycle | SSM-120 | Functionality | YES | User | SmartSource | Access and submit Savings form | Create a link between approvals and Sourcing project | Savings form will be added to Project Succesfully | Savings form will be added to Project Succesfully | Mark Silvestrin | Jason Ungeran | Sourcing | TO TEST |  |  | BMO Harris N.A.
121 | SSM | Sourcing project and event management lifecycle | SSM-121 | Functionality |  | BAU | SmartSource | Sourcing Project Tasks | Initiate Sourcing Project tasks approvals. | Only able to add someone in the approval chain as approver/watcher if they have been setup in BMO SmartProcure | Project Task Approval to be completed | Mark Silvestrin | Jason Ungeran | Sourcing | TO TEST |  |  | BMO Harris N.A.
122 | SSM | Sourcing project and event management lifecycle | SSM-122 | Functionality |  | BAU | SmartSource | Promoting and demoting Members | Test Memeber - promoting and demoting |  | Promotion and demotion of project members | Mark Silvestrin | Jason Ungeran | Sourcing | TO TEST |  |  | BMO Harris N.A.
123 | CMO | Contract lifecycle management processes | CMO-123 | Functionality | YES | User | CLM | Access to CLM, basic functionality |  |  | Contract Application has no regression | Shivana Mohammed​ | Dan Muldoon | CMO | TO TEST |  |  | BMO Harris N.A.
124 | CMO | Contract lifecycle management processes | CMO-124 | Functionality | YES | LENC | CLM | Activating contract - check in Coupa Core |  |  | Contract Application has no regression | Shivana Mohammed​ | Dan Muldoon | CMO | TO TEST |  |  | BMO Harris N.A.
125 | PES | AP processing lifecycle- Contract update | PES-125 | Functionality | YES | LENC | Coupa | Contract Update | Contract updates | Changed the Expiration Date and Maximum Spend | Contract Updated | Judy Nguyen | Martin Vermette | PES | TO TEST |  |  | BMO Harris N.A.
126 | LA | User Setup Processes | LA-126 | Functionality | YES | User | Coupa | Setup New User manually by clicking on ‘Create’ | Setup New User manually by clicking on ‘Create’ | User will be created successfully | User will be created successfully | Daphne Delefes / Allesha Bryce/Daniella Kurash | Kavitha Nagaraja | Logical Access | TO TEST |  |  | BMO Harris N.A.
127 | LA | User Setup Processes | LA-127 | Functionality |  | BAU | Coupa | Remove Expense License and Expense User Role | Remove Expense License and Expense User Role | Expense License and role will be removed successfully | Expense License and role will be removed successfully | Daphne Delefes / Allesha Bryce/Daniella Kurash | Kavitha Nagaraja | Logical Access | TO TEST |  |  | BMO Harris N.A.
128 | LA | User Setup Processes | LA-128 | Functionality | YES | User | Coupa | Add an Expense Delegate | Add an Expense Delegate | Expense delegate will be added successfully | Expense delegate will be added successfully | Daphne Delefes / Allesha Bryce/Daniella Kurash | Kavitha Nagaraja | Logical Access | TO TEST |  |  | BMO Harris N.A.
129 | LA | User Setup Processes | LA-129 | Functionality | YES | User | Coupa | Add an Approval Delegate | Add an Approval Delegate | Approval delegate will be added successfully | Approval delegate will be added successfully | Daphne Delefes / Allesha Bryce/Daniella Kurash | Kavitha Nagaraja | Logical Access | TO TEST |  |  | BMO Harris N.A.
130 | LA | User Setup Processes | LA-130 | Functionality | YES | User | Coupa | Upload a new user from Upload File | Upload a new user from Upload File | Upload will be successful and new user created | Upload will be successful and new user created | Daphne Delefes / Allesha Bryce/Daniella Kurash | Kavitha Nagaraja | Logical Access | TO TEST |  |  | BMO Harris N.A.
131 | LA | User Setup Processes | LA-131 | Functionality |  | BAU | Coupa | Deactivate a Profile | Deactivate a Profile | Profile will be inactive | Profile will be inactive | Daphne Delefes / Allesha Bryce/Daniella Kurash | Kavitha Nagaraja | Logical Access | TO TEST |  |  | BMO Harris N.A.
132 | LA | User Setup Processes | LA-132 | Functionality |  | BAU | Coupa | Reactivating a User from Upload File (testing specifically to see if previous roles are removed) | Reactivating a User from Upload File (testing specifically to see if previous roles are removed) | Previous roles (ie. User) will be removed after upload | Previous roles (ie. User) will be removed after upload | Daphne Delefes / Allesha Bryce/Daniella Kurash | Kavitha Nagaraja | Logical Access | TO TEST |  |  | BMO Harris N.A.
133 | SE-E2E | Supplier Enablement and Setup processes | SE-E2E-133 | E2E | YES | LENC, CG | Oracle-IDP-Coupa-CLM | New Supplier- Setup Of Us Address | New Supplier- Setup Of Us Address Oracle To Coupa Integration Is Succesful | - SRM Setups In Oracle And Allows 24 Hours F Or Integration | Oracle To Coupa Integration Is Succesful | Rachel Fima | Martin Vermette | SE | TO TEST | SRM Officer |  | BMO Harris N.A. |  |  |  |  | Not Applicable | Not Applicable | Not Applicable
134 | SE-E2E | Supplier Enablement and Setup processes | SE-E2E-134 | E2E | YES | LENC, CG | Oracle-IDP-Coupa-CLM | New Supplier-Setup Of Canadian Address | New Supplier-Setup Of Canadian Address | - SRM Setups In Oracle And Allows 24 Hours F Or Integration | Oracle To Coupa Integration Is Succesful | Rachel Fima | Martin Vermette | SE | TO TEST | SRM Officer |  | BMO Harris N.A. |  |  |  |  | Not Applicable | Not Applicable | Not Applicable
135 | SE-E2E | Supplier Enablement and Setup processes | SE-E2E-135 | E2E | YES | LENC, CG | Oracle-IDP-Coupa-CLM | New Supplier- Setup Of International Address | New Supplier- Setup Of International Address | - SRM Setups In Oracle And Allows 24 Hours F Or Integration | Oracle To Coupa Integration Is Succesful | Rachel Fima | Martin Vermette | SE | TO TEST | SRM Officer |  | BMO Harris N.A. |  |  |  |  | Not Applicable | Not Applicable | Not Applicable
136 | SE-E2E | Supplier Enablement and Setup processes | SE-E2E-136 | E2E | YES | LENC, CG | Oracle-IDP-Coupa-CLM | New Supplier- Setup CLMA Shell Supplier | New Supplier- Setup Clma Shell Supplier | Supplier Type= CLMA | SRM Sets Up Shell Supplier and Profile Will Not Load Into Smartprocure | Rachel Fima | Martin Vermette | SE | TO TEST | SRM Officer |  | BMO Harris N.A. |  |  |  |  | Not Applicable | Not Applicable | Not Applicable
137 | SE-E2E | Supplier Enablement and Setup processes | SE-E2E-137 | E2E | YES | LENC, CG | Oracle-IDP-Coupa-CLM | BoTW Restriction Contrent group | Setup supplier with BoTW |  |  | Rachel Fima | Martin Vermette | SE | TO TEST
138 | SE-E2E | Supplier Enablement and Setup processes | SE-E2E-138 | E2E |  | BAU | Oracle-IDP-Coupa-CLM | Add New Site To Existing Supplier | Add New Site To Existing Supplier | Remit To Address Available | Oracle To Coupa Integration Is Succesful | Rachel Fima | Martin Vermette | SE | TO TEST | SRM Officer |  | BMO Harris N.A. |  |  |  |  | Not Applicable | Not Applicable | Not Applicable
139 | SE-E2E | Supplier Enablement and Setup processes | SE-E2E-139 | E2E |  | BAU | Oracle-IDP-Coupa-CLM | Reactivation Of Supplier/Site In Oracle | Reactivation Of Supplier/Site In Oracle | Remit To/ Supplier Should Active In Coupa | Oracle To Coupa Integration Is Succesful | Rachel Fima | Martin Vermette | SE | TO TEST | SRM Officer |  | BMO Harris N.A. |  |  |  |  | Not Applicable | Not Applicable | Not Applicable
140 | SE-E2E | Supplier Enablement and Setup processes | SE-E2E-140 | E2E |  | BAU | Oracle-IDP-Coupa-CLM | Po Email / Match Level Add Request | Po Email / Match Level Add Request | SRM Updates Oracle With Po Email And In 24 Hours Confirms Integration And Updates Po Method And Po Change Method Field From “Prompt” To “Email” | Oracle To Coupa Integration Is Succesful | Rachel Fima | Martin Vermette | SE | TO TEST | SRM Officer |  | BMO Harris N.A. |  |  | Tax , Commodity, Location Code |  | Not Applicable | Not Applicable | Not Applicable
141 | SE | Supplier Enablement and Setup processes | SE-141 | Functionality |  | BAU | Coupa | Invoice Inbox | Invoice Inbox - email, assign to/archive, confirm email audomatically added to profile/add another email directly, view drop down, export | 1. invoices@bmo-test.coupahost.com | Invoice Inbox Process Is Successful | Rachel Fima | Martin Vermette | SE | TO TEST | AP Officer |  | BMO Harris N.A. |  |  |  |  | Not Applicable | Not Applicable | Not Applicable
142 | SE | Supplier Enablement and Setup processes | SE-142 | Functionality |  | BAU | Coupa | Invoice Tab | Invoice Tab - export button, edit/comments/ok to process (completed), edit/comments/ok to process ( reject) |  | Invoices Process Is Successful | Rachel Fima | Martin Vermette | SE | TO TEST |  |  | BMO Harris N.A. |  |  |  |  | Not Applicable | Not Applicable | Not Applicable
143 | SE | Supplier Enablement and Setup processes | SE-143 | Functionality |  | BAU | Coupa | CSP Setup | CSP Setup | Csp Setup Is Successful And Allows Link | Initiation Of Invitation To Self , Confirm Linked After Setup Completed. | Rachel Fima | Martin Vermette | SE | TO TEST |  |  | BMO Harris N.A. |  |  |  |  | Not Applicable | Not Applicable | Not Applicable
144 | SE | Supplier Enablement and Setup processes | SE-144 | Functionality |  | BAU | Coupa | Tymetrix Settings | Tymetrix Settings | Do Tymetrix Setting Setups | Tymetrix Settings Can Be Successfully Set Up | Rachel Fima | Martin Vermette | SE | TO TEST |  |  | BMO Harris N.A. |  |  |  |  | Not Applicable | Not Applicable | Not Applicable
145 | Supp-E2E | Manitenance /Support | Supp-E2E-145 | E2E |  | BAU | Oracle-IDP-Coupa | Cost Centre / G/L Updates | To set up / update a cost centre or G/L in Oracle that will be updated in Coupa next day. | One day waiting time | CC and GL updated in Coupa | Carlos Alcazar | Suhail Durrani | DTS | TO TEST
146 | Supp-E2E | Manitenance /Support | Supp-E2E-146 | E2E | YES | User | Oracle-IDP-Coupa | Custom Requisition and Invoice approval chains | Submit a BR related request to verify custom approval chains and approve | Tested Request, change order and Invoice approval chains. | Custom approval works as intended | Binh Tran | Suhail Durrani | DTS | TO TEST
147 | Supp | Manitenance /Support | Supp-147 | Functionality |  | BAU | Coupa | Coupa reporting (running, scheduling) | Schedule and run standard reports |  |  | Carlos Alcazar | Suhail Durrani | DTS | TO TEST
148 | Supp | Manitenance /Support | Supp-148 | Functionality |  | BAU | Coupa | Coupa App | Create an Exp on computer and verify on app |  | Exp Report created on computer/web app shows in Mobile app | Carlos Alcazar | Suhail Durrani | DTS | TO TEST
149 | Supp | Manitenance /Support | Supp-149 | Functionality |  | BAU | Coupa | Coupa App | Submit an expense report on app and approve on computer |  |  | Carlos Alcazar | Suhail Durrani | DTS | TO TEST
150 | Supp | Manitenance /Support | Supp-150 | Functionality |  | BAU | Coupa | Coupa App | Create an Exp on app and verify on computer |  |  | Carlos Alcazar | Suhail Durrani | DTS | TO TEST
151 | Supp | Manitenance /Support | Supp-151 | Functionality |  | BAU | Coupa | Coupa App | Submit an expense report on computer and approve on app |  |  | Carlos Alcazar | Suhail Durrani | DTS | TO TEST
152 | Supp | Manitenance /Support | Supp-152 | Functionality | YES | LENC, SUBS/PG | Coupa | CSV INV upload | Invoice upload via UI | Upload a CSV invoice data file via 'Load from file' |  | Binh Tran | Suhail Durrani | DTS | TO TEST
153 | Supp | Manitenance /Support | Supp-153 | E2E | YES | NEW PUCHOUTS | Coupa-IDP-Oracle-Suppl | Buyer Portal checks | Test links (internal), the "Can't Find..looking for" Form | Tested Punch out sites, forms, catalogs and policies | Ability to create Requests from forms, policies and punch out site | Binh Tran | Suhail Durrani | DTS | TO TEST
154 | Supp | Manitenance /Support | Supp-154 | Functionality | YES | CG | Coupa | Supplier search | Test supplier search on Invoice Form, Web form, Invoices, Requisitions |  |  | Carlos Alcazar | Suhail Durrani | DTS | TO TEST
155 | Supp | Manitenance /Support | Supp-155 | FUNC TESTING | YES | LENC, SUBS/PG | Coupa | CSP Submission | Submit invoice to Coupa using CSP |  |  | Carlos Alcazar | Suhail Durrani | DTS | TO TEST
156 | Supp | Manitenance /Support | Supp-156 | FUNC TESTING | YES | LENC, SUBS/PG | Coupa | CXML Submission (punchout?) | Submit invoice to Coupa from a punchout supplier |  |  | Binh Tran | Suhail Durrani | DTS | TO TEST
157 | Supp | Manitenance /Support | Supp-157 | FUNC TESTING | YES | LENC, SUBS/PG | Coupa | CSV upload internat sftp | Submit invoice to Coupa using CSV uploads |  |  | Binh Tran | Suhail Durrani | DTS | TO TEST
158 | Supp | Manitenance /Support | Supp-158 | Functionality |  | BAU | Coupa | Invoice Inbox | Submit invoice to Coupa using the inbox emails | Submitted Invoices to CAN and AP invoice inbox | Downloading Invoices from Inbox successful. Notifications generated when we sent to the supplier | Carlos Alcazar | Suhail Durrani | DTS | TO TEST
159 | Supp | Manitenance /Support | Supp-159 | Functionality |  | BAU | Coupa | Sourcing and CLM | General testing . E.g. Reporting | Tested reporting capabilities, event and contract creation |  | Shawn Ambrose | Suhail Durrani | DTS | TO TEST
160 | Supp | Manitenance /Support | Supp-160 | Functionality |  | BAU | Coupa | Coupa App | To capture expense line with receipt photo on mobile app |  | The expense line with details | Carlos Alcazar | Suhail Durrani | DTS | TO TEST
161 | Supp | Manitenance /Support | Supp-161 | Functionality | YES | LENC | Coupa | PO Layout | Generate PO file going out to supplier |  | PO layount in email attchement is not changed | Carlos Alcazar | Suhail Durrani | DTS | TO TEST
162 | EXP-E2E | Corporate cards and Expense processes | EXP-E2E-162 | E2E | YES | LENC, User | Coupa-IDP-Oracle | MC transaction-Tax Validation | Approval chain for Harris users Act as employee who creates expense report Expense report XXX has been generated with card transactions; add one out-of-pocket charge ($100) and categorize all card & out-of-pocket as business transactions. Itemize charges between two Harris Sub Accounts (Cost Centres). Containing at least one Mast Card Charge and at least one cash charge | 1. Act as Approver to Approve Expense 2. | Approved expense report Flow to Oracle OIT Taxes applied | Kirstie Haisley / Dyanne Tully/ SDS | Martin /Tiffany | Cards/AP | TO TEST |  |  | BMO Harris N.A.
163 | EXP-E2E | Corporate cards and Expense processes | EXP-E2E-163 | E2E |  | BAU | Coupa-IDP-Oracle | BMO | Enter expense lines per province code. | Each province code generates respective tax combination per province. There should be at least 10 lines on the expense report. Specific categories to be tested. | One expense can have muplitple expense line one per province | Kirstie Haisley / Dyanne Tully/ SDS | Martin /Tiffany | Cards/AP | TO TEST |  |  | BMO Harris N.A.
164 | EXP-E2E | Corporate cards and Expense processes | EXP-E2E-164 | E2E |  | BAU | Coupa-IDP-Oracle | NB | Enter expense lines per province code. | Each province code generates respective tax combination per province. There should be at least 10 lines on the expense report. Specific categories to be tested. | One expense can have muplitple expense line one per province | Kirstie Haisley / Dyanne Tully/ SDS | Martin /Tiffany | Cards/AP | TO TEST |  |  | BMO Harris N.A.
165 | EXP-E2E | Corporate cards and Expense processes | EXP-E2E-165 | Functionality |  | BAU | Coupa-Oracle | MC transaction | General Expense Report (French) Create an expense report for a Canadian user. | Expense report XXX has been generated with card transactions; add one out-of-pocket charge ($100) and categorize at least 1 card & out-of-pocket as business transactions and at least 1 card transaction as personal charge. | The same G/L and cost centre is populated on line 2 | Kirstie Haisley / Dyanne Tully/ SDS | Martin /Tiffany | Cards/AP | TO TEST |  |  | BMO Harris N.A.
166 | EXP | Corporate cards and Expense processes | EXP-166 | Functionality |  | BAU | Coupa-Oracle | Copy account function | Expense report XXX has been generated with 2 out-of-pocket expense lines. The first line's account is populated by the expense category "Airfare" while the account is populated by the "copy from above" function Create an expense report with more than one expense line for employee with copy from above function enabled |  | Approved expense report | Kirstie Haisley / Dyanne Tully/ SDS | Martin /Tiffany | Cards/AP | TO TEST |  |  | BMO Harris N.A.
167 | EXP | Corporate cards and Expense processes | EXP-167 | Functionality |  | BAU | Coupa-Oracle | ER not requiring approval | Create an expense report for with credit out of pocket line totaling the card transaction amounts to create a zero dollar ER | Expense report XXX has been generated with card transactions; add one out-of-pocket charge that totals the card transactions but in credit. Categorize all card transactions as business and out of pocket credit as personal. Expense report will be routed to manager for approval | Approved expense report | Kirstie Haisley / Dyanne Tully/ SDS | Martin /Tiffany | Cards/AP | TO TEST |  |  | BMO Harris N.A.
168 | EXP | Corporate cards and Expense processes | EXP-168 | Functionality |  | BAU | Coupa-Oracle | Send Expense Lines Back to the Submitter | Create an expense report with more than one expense line | Expense report XXX has been generated with 1 out-of-pocket and 1 card transaction lines. Select expense categories Airfare and Food and Beverage (Business Travel) using the default cost centre then submit for approval. | Approved expense report | Kirstie Haisley / Dyanne Tully/ SDS | Martin /Tiffany | Cards/AP | TO TEST |  |  | BMO Harris N.A.
169 | EXP | Corporate cards and Expense processes | EXP-169 | Functionality |  | BAU | Coupa-Oracle | Submission blocker | Submission blocker for Procurement Cost Centre Create an expense report for (that is not a procurement employee) in the amount of $1000, where the cost centre is H9213 | Expense report XXX has been generated with card transactions; add one out-of-pocket charge ($100) and categorize all card & out-of-pocket as business transactions. Code all transaction lines to cost centre H9213. The expense report will be blocked at submission. | Approved expense report | Kirstie Haisley / Dyanne Tully/ SDS | Martin /Tiffany | Cards/AP | TO TEST |  |  | BMO Harris N.A.
170 | EXP | Corporate cards and Expense processes | EXP-170 | Functionality |  | BAU | Coupa | Special groups | Approval chain for Medical Nurse category Create an expense report for any amount, with any user and select category "Executive Medical Expenses" | Expense report XXX has been generated with card transactions; add one out-of-pocket charge ($100) and categorize all card & out-of-pocket as business transactions. Do not change the defaulted cost centre. Expense report will be routed to Medical Nurse Approval group. | Approved expense report | Kirstie Haisley / Dyanne Tully/ SDS | Martin /Tiffany | Cards/AP | TO TEST |  |  | BMO Harris N.A.
171 | EXP | Corporate cards and Expense processes | EXP-171 | Functionality |  | BAU | Coupa | Special groups | Approval chain for WPA Create an expense report for a Canadian user where account contains Cost Centre Bank of Montreal H5043. | Expense report XXX has been generated with card transactions; add one out-of-pocket charge ($100) and categorize all card & out-of-pocket as business transactions. Code all transaction lines to cost centre H5043. Expense report will be routed to "WPA Manager" only for approval, no additional approvals required. | Accounts Payable BA group will receive the expense report and will reject | Kirstie Haisley / Dyanne Tully/ SDS | Martin /Tiffany | Cards/AP | TO TEST |  |  | BMO Harris N.A.
172 | EXP | Corporate cards and Expense processes | EXP-172 | Functionality |  | BAU | Coupa | Special groups | Approval chain for Executive Dining Create an expense report for an USD user, category Food and Beverage(Business Travel) and Food and Beverage(Internal Use), line description is "exec_dining" | Expense report XXX has been generated with card transactions; add one out-of-pocket charge ($100) and categorize all card & out-of-pocket as business transactions. Choose expense category Food and Beverage (Business Travel) and Food and Beverage (Internal Use) and change the transaction description to "exec_dining". Expense report will be routed to Coupa custom executive dining approval group for approval Containing at least one Mast Card Charge and at least one cash charge | Approved expense report | Kirstie Haisley / Dyanne Tully/ SDS | Martin /Tiffany | Cards/AP | TO TEST |  |  | BMO Harris N.A.
173 | EXP-E2E | Corporate cards and Expense processes | EXP-E2E-173 | Functionality | YES | TAX | Coupa-Oracle | Cross Currency | Cross Currency Create an expense report for a Canadian user and select Harris cost centre | Expense report XXX has been generated with card transactions; add one out-of-pocket charge ($100) and categorize all card & out-of-pocket as business transactions. Change the cost centre to 00324 under Harris company #10. Expense report will be routed to accounts payable BA group for approval, then to the chain of approvers. | Approved expense report | Kirstie Haisley / Dyanne Tully/ SDS | Martin /Tiffany | Cards/AP | TO TEST |  |  | BMO Harris N.A.
174 | EXP-E2E | Corporate cards and Expense processes | EXP-E2E-174 | Functionality | YES | TAX | Coupa-Oracle | Cross Entity | Cross Entity within the same currency Create an expense report for a Canadian user and select Nesbitt cost centre | Expense report XXX has been generated with card transactions; add one out-of-pocket charge ($100) and categorize all card & out-of-pocket as business transactions. Change the cost centre to UNITES (destination NTLTD) under Nesbitt Burns OU. | Expense line 1 is sent back to the submitter in a brand new expense report XYZ, with expense line 2 fully approved for payment | Kirstie Haisley / Dyanne Tully/ SDS | Martin /Tiffany | Cards/AP | TO TEST |  |  | BMO Harris N.A.
175 | PUR | Purchasing lifecycle | PUR-175 | Functionality | YES | LENC | Coupa | Forecast PO | Create a forecast PO to ensure template is correct | any supplier |  | Sri Sinnathurai | Martin Vermette | Purchasing | TO TEST |  |  | BMO Harris N.A.
176 | PUR | Purchasing lifecycle | PUR-176 | Functionality | NO | BAU | Coupa | change order | edit change a PO supplier, which cancels the original PO and issues a new PO | create BMO CAD PO for NICE SYSTEMS, INC, and edit change the supplier to NICE SYSTEMS CANADA LTD |  | Sri Sinnathurai | Martin Vermette | Purchasing | TO TEST |  |  | BMO Harris N.A.
177 | PUR | Purchasing lifecycle | PUR-177 | Functionality | NO | BAU | Coupa | quantity base PO | create requisition with quantity 1 and AP attempt to match more than 1 invoice | AP to test |  | Sri Sinnathurai | Martin Vermette | Purchasing | TO TEST |  |  | BMO Harris N.A.
178 | PUR | Purchasing lifecycle | PUR-178 | Functionality | NO | BAU | Coupa | credit and rebill | create PO for quantity based" and have AP match invoice, then credit then match a new invoice | create Hewlett Packard PO for $10,000, AP matches invoice for $9,000, then a credit for $9,000, then a new invoice for $10,000 |  | Sri Sinnathurai | Martin Vermette | Purchasing | TO TEST |  |  | BMO Harris N.A.
179 | PUR | Purchasing lifecycle | PUR-179 | Functionality | NO | BAU | Coupa | credit and rebill | create PO for "amount based" and have AP match invoice, then credit then match a new invoice | create Hewlett Packard PO for $10,000, AP matches invoice for $9,000, then a credit for $9,000, then a new invoice for $10,000 |  | Sri Sinnathurai | Martin Vermette | Purchasing | TO TEST |  |  | BMO Harris N.A.
180 | PUR | Purchasing lifecycle | PUR-180 | Functionality | NO | BAU | Coupa | unsent PO | create a PO with supplier that does not have a PO email contact in supplier record |  |  | Sri Sinnathurai | Martin Vermette | Purchasing | TO TEST |  |  | BMO Harris N.A.
181 | INV | AP processing lifecycle | INV-181 | Functionality | NO | BAU | Coupa | Non-back Invoice, Cross-border | 1. Non-back scanned Invoice, cross-border , Checking comment request 2. Canadian supplier with USD currency. 3. AP processor keys mandatory fields on Invoice header: Supplier, Invoice #, Invoice Date, Currency, Invoice Control Total, Chart of Accounts, Remit To, Invoice Approver, Route Invoice for Comment Mandatory fields on line level: Line Level Taxation, Description, QTY, Price, Select Tax, Project Number. Enters XXXX.XXXX.XXXX in billing. 4. Enter comments @user asking NRWT instructions 5. Submit. 6. Approver gets notification, Opens invoices, changes billing account, Approves. 7. Second approver gets notification, Opens invoice, add NRWT comments, Approves. 8. Invoice status = Pending Approval with AP group, 9. AP processor opens the invoice, applies WITHHOLDING TAX, and Self Assess Tax, Approves , Invoice status = Approved. | Start with any Draft invoice, Currency USD, Comments to user | Comments flow back and force, AP group as last approver, Withholding tax, status Approved. Expected to get load in Oracle, with NRWT and SAONHST tax code and in FA module as well | Dyanne Tully/ Sebastien Martel | Tiffany Sadler | AP | TO TEST |  |  | BMO Harris N.A.
182 | INV | AP processing lifecycle | INV-182 | Functionality | NO | BAU | Coupa | Apply invoice attribute, check in Views | 1. Apply invoice attribute, verify in the view. E.g. 2.Apply invoice attribute 'Issue'. 3.check the invoice in the view (CA) Attribute - Issue | Any invoice with status Draft, On Hold, AP Hold … | Attribute applied | Dyanne Tully/ Sebastien Martel | Tiffany Sadler | AP | TO TEST |  |  | BMO Harris N.A.
183 | INV | AP processing lifecycle | INV-183 | Functionality | NO | BAU | Coupa | AP Inbox Archive | Invoice inbox Archive view: To prevent any accidents with deleting invoices that are distributed between AP teams, we've introduced an invoice inbox archive. | Verify if there is an Archive view in the Inbox module | Archive view in the Inbox module | Dyanne Tully/ Sebastien Martel | Tiffany Sadler | AP | TO TEST |  |  | BMO Harris N.A.
184 | INV-E2E | AP processing lifecycle | INV-E2E-184 | E2E | YES | LENC, SUBS, CC | Coupa-IDP-Oracle | Basic flow for NON-PO invoice | AP processor choose draft invoice, complete mandatory fields, negative $ amount, submit to user with XXXX-XXXXX-XXXX accounting. Submit. Status Pending approval by user. User enters accounting and approves Status Approved | Start from draft invoice. Total amount less -$100 | Pending Approval | Dyanne Tully/ Sebastien Martel | Tiffany Sadler | AP | TO TEST |  |  | BMO Harris N.A.
185 | INV | AP processing lifecycle | INV-185 | Functionality | YES | TBD | Coupa | Payment request form | Create a payment request, using the new form. | 1-Retrieve the form from the Homepage 2-complete the form 3-Choose Umer as approver 4-Submit the form 5-Retrieve the form, complete AP portion submit to Approver Umer 6- Act as Umer and approve the invoice | Invoice get approved | Dyanne Tully/ Sebastien Martel | Tiffany Sadler | AP | TO TEST |  |  | BMO Harris N.A.
186 | INV | AP processing lifecycle | INV-186 | Functionality | NO | BAU | Coupa | Credit Invoice | create credit note invoice | Start from draft invoice | Invoice approved | Dyanne Tully/ Sebastien Martel | Tiffany Sadler | AP | TO TEST |  |  | BMO Harris N.A.
187 | INV | AP processing lifecycle | INV-187 | Functionality | NO | BAU | Coupa | Check Filters | Check Coupa Filter vs table |  |  | Dyanne Tully/ Sebastien Martel | Tiffany Sadler | AP | TO TEST |  |  | BMO Harris N.A.
188 | INV | AP processing lifecycle | INV-188 | Functionality | NO | BAU | Coupa | From the On Hold view see if there is tolerance failed. | PO quantity tolerance | system to flag tolerance | On Hold vs Pending Approval | Dyanne Tully/ Sebastien Martel | Tiffany Sadler | AP | TO TEST |  |  | BMO Harris N.A.
189 | INV | AP processing lifecycle | INV-189 | Functionality | NO | BAU | Coupa | Duplicate invoice verification | Enter a duplicate invoice # to validate if the duplicate flag prior submit is still working | start with draft invoice and key in duplicate submission | Supplier; DELL MARKETING LP Invoice #TESTINV-134 invoice flagged as duplicate prior to hitting submit | Dyanne Tully/ Sebastien Martel | Tiffany Sadler | AP | TO TEST |  |  | BMO Harris N.A.
190 | INV | AP processing lifecycle | INV-190 | Functionality | NO | BAU | Coupa | Reject and Dispute flow for NON-BACK invoice - Reject, Dispute, and Void | 1. Reject and Dispute flow for NON-BACK scanned invoice with one approver AP processor selects non backed invoices from the Coupa Draft (CA/US) Kofax. 2. Enters Mandatory fields on Invoice header: Supplier, Invoice #, Invoice Date, Currency, Invoice Control Total, Chart of Accounts, Remit To, Invoice Approver. Mandatory fields on line level: Line Level Taxation, Description, QTY, Price, Select Tax. Enters XXXX.XXXX.XXXX in billing. Submit. 3. Approver gets notification, Opens invoices, Rejects invoice. Invoice status = Rejected 4. AP processor opens invoice from Rejects view, Click Dispute, enters supplier's address, comments, choose Dispute reason. Invoices status - Disputed 5. Go to Disputes to Void view, and void this invoice. | Choose invoice with Draft status | Invoices status - Disputed | Dyanne Tully/ Sebastien Martel | Tiffany Sadler | AP | TO TEST |  |  | BMO Harris N.A.
191 | INV | AP processing lifecycle | INV-191 | Functionality | NO | BAU | Coupa | Alternative approver, NON-BACK scanned invoice | Alternative approver, NON-BACK scanned invoice AP processor selects non backed invoices from the Coupa Draft (CA/US) Kofax. Enters Mandatory fields on Invoice header: Supplier, Invoice #, Invoice Date, Currency, Invoice Control Total, Chart of Accounts, Remit To, Invoice Approver. Mandatory fields on line level: Line Level Taxation, Description, QTY, Price, Select Tax. Enters XXXX.XXXX.XXXX in billing. Submit. Approver1 gets notification, opens invoices, changes billing account, Enters Alternative approver, Approves. Invoice status = Pending Approval Alternative approver get notification, opens invoices, Approves. Invoice status = Approved | Choose invoice with Draft status | Invoice to flow to Alternative approver , get Approved | Dyanne Tully/ Sebastien Martel | Tiffany Sadler | AP | TO TEST |  |  | BMO Harris N.A.
192 | INV | AP processing lifecycle | INV-192 | Functionality | NO | BAU | Coupa | NON-PO Inbox invoice with Multiple approvers approver | 1. Basic flow for NON-PO scanned invoice with Multiple approvers approver 2. AP Processor selects non backed invoices from the Coupa Draft (CA/US) Kofax. Enters Mandatory fields on Invoice header: Supplier, Invoice #, Invoice Date, Currency, Invoice Control Total, Chart of Accounts, Remit To, Invoice Approver. Mandatory fields on line level: Line Level Taxation, Description, QTY, Price, Select Tax. Enters XXXX.XXXX.XXXX in billing. Submit. 3. Approver1 get notification, opens invoices, changes billing account, Approves. 4. Invoice status = Pending Approval 5. Approver2 get notification, opens invoices, Approves. 6. Invoice status = Approved | Start with any Draft invoice, invoice amount over $5000 | Multiple approvers, Invoice Approved | Dyanne Tully/ Sebastien Martel | Tiffany Sadler | AP | TO TEST |  |  | BMO Harris N.A.
193 | INV | AP processing lifecycle | INV-193 | Functionality | NO | BAU | Coupa | Validate if the TECH FINANCE approval group is behaving as expected | Approval limit should be 0$, if no approver with limit, it should go to UA | Try to approve with no approver with limit added. + add an approver. | Invoice routed to respective approval group. | Dyanne Tully/ Sebastien Martel | Tiffany Sadler | AP | TO TEST |  |  | BMO Harris N.A.
194 | INV | AP processing lifecycle | INV-194 | Functionality | NO | BAU | Coupa | Validate if the BMO FAMILY OFFICE approval group is behaving as expected | Approval limit should be 0$, if no approver with limit, it should go to UA | Try to approve with no approver with limit added. + add an approver. | Invoice routed to respective approval group. | Dyanne Tully/ Sebastien Martel | Tiffany Sadler | AP | TO TEST |  |  | BMO Harris N.A.
195 | INV | AP processing lifecycle | INV-195 | Functionality | NO | BAU | Coupa | Validate if the INFRASTRUCTURE ACCOUNTING approval group is behaving as expected | Approval limit should be 0$, if no approver with limit, it should go to UA | Try to approve with no approver with limit added. + add an approver. | Invoice routed to respective approval group. | Dyanne Tully/ Sebastien Martel | Tiffany Sadler | AP | TO TEST |  |  | BMO Harris N.A.
196 | INV | AP processing lifecycle | INV-196 | Functionality | YES | TBD | Coupa | BLOTTER: create an invoice - | Create an entry under supplier BLOTTER, name in accordance to blotter convention, date, COA, and Remit all should be filled in as a blotter entry, and then save. Determine if this populates in SmartProcure through an advanced search afterwards. | Manually create an invoice | from NEW to Pending Approval | Dyanne Tully/ Sebastien Martel | Tiffany Sadler | AP | TO TEST |  |  | BMO Harris N.A.
197 | INV | AP processing lifecycle | INV-197 | Functionality | NO | BAU | Coupa | AP Inbox: Create and invoice from AP Inbox | Take an existing AP Inbox entry - create into an invoice and add all relevant information | Invoice to be created from the AP Inbox | Pending Approval | Dyanne Tully/ Sebastien Martel | Tiffany Sadler | AP | TO TEST |  |  | BMO Harris N.A.
198 | INV | AP processing lifecycle | INV-198 | Functionality | NO | BAU | Coupa | Spend guard; with the upgrade, we should now getting only invoices that are potentially ''duplicate''. Duplicate invoice detected should not be in ''voided'' status |  | Invoice to be capture in the Spend guard view. If required, create duplicate invoices to test the application | 1- No invoice with a status ''voided'' 2- If possible duplicate, invoice should get flag by the system and be sent to the Approval SG for review | Dyanne Tully/ Sebastien Martel | Tiffany Sadler | AP | TO TEST |  |  | BMO Harris N.A.
199 | INV | AP processing lifecycle | INV-199 | Functionality | NO | BAU | Coupa | Orders - Split screen | To view the split screen capability showing related docs to the PO. The 'Related Doc' icon is located on the top right corner of the screen. | AP Review. If AP want this access it can be added to the BMO AP & AP admin roles. | View and access related invoice documents | Dyanne Tully/ Sebastien Martel | Tiffany Sadler | AP | TO TEST |  |  | BMO Harris N.A.
200 | PAY | AP processing lifecycle - Payments | PAY-200 | Functionality | NO | BAU | Oracle | Add / Remove manual hold |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
201 | PAY | AP processing lifecycle - Payments | PAY-201 | Functionality | NO | BAU | Oracle | Add internal note at invoice level |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
202 | PAY | AP processing lifecycle - Payments | PAY-202 | Functionality | NO | BAU | Oracle | Add payment description / void reason |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
203 | PAY | AP processing lifecycle - Payments | PAY-203 | Functionality | NO | BAU | Oracle | Cancel an invoice |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
204 | PAY | AP processing lifecycle - Payments | PAY-204 | Functionality | NO | BAU | Oracle | Cancel a payment / invoice |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
205 | PAY | AP processing lifecycle - Payments | PAY-205 | Functionality | NO | BAU | Oracle | Remove check from batch prior to payment |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
206 | PAY | AP processing lifecycle - Payments | PAY-206 | Functionality | YES | SUBS/PG | Oracle | Change pay group |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
207 | PAY | AP processing lifecycle - Payments | PAY-207 | Functionality | YES | SUBS/PG | Oracle | Change payment method |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
208 | PAY | AP processing lifecycle - Payments | PAY-208 | Functionality | NO | BAU | Oracle | Close / Open control g/l period |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
209 | PAY | AP processing lifecycle - Payments | PAY-209 | Functionality | NO | BAU | Oracle | Close / Sweep invoices to next accounting period |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
210 | PAY | AP processing lifecycle - Payments | PAY-210 | Functionality | NO | BAU | Oracle | Create batch set |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
211 | PAY | AP processing lifecycle - Payments | PAY-211 | Functionality | NO | BAU | Oracle | Issue Future dated payment |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
212 | PAY | AP processing lifecycle - Payments | PAY-212 | Functionality | NO | BAU | Oracle | Open next accounting period |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
213 | PAY | AP processing lifecycle - Payments | PAY-213 | Functionality | YES | TBD | Oracle | Process manual payments: |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
214 | PAY | AP processing lifecycle - Payments | PAY-214 | Functionality | NO | BAU | Oracle | Remove one invoice from payment batch |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
215 | PAY | AP processing lifecycle - Payments | PAY-215 | Functionality | NO | BAU | Oracle | Run / Schedule Approval job |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
216 | PAY | AP processing lifecycle - Payments | PAY-216 | Functionality | NO | BAU | Oracle | Run Create Accounting |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
217 | PAY | AP processing lifecycle - Payments | PAY-217 | Functionality | NO | BAU | Oracle | Run Accounts payable Trial balance report |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
218 | PAY | AP processing lifecycle - Payments | PAY-218 | Functionality | NO | BAU | Oracle | Run ARS/IPS extract |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
219 | PAY | AP processing lifecycle - Payments | PAY-219 | Functionality | NO | BAU | Oracle | Run GL Transfer (spool) |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
220 | PAY | AP processing lifecycle - Payments | PAY-220 | Functionality | NO | BAU | Oracle | Run payable account Invoice on Hold |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
221 | PAY | AP processing lifecycle - Payments | PAY-221 | Functionality | NO | BAU | Oracle | Run payment batch for : EFT from US |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
222 | PAY | AP processing lifecycle - Payments | PAY-222 | Functionality | NO | BAU | Oracle | Run payment batch for : CAD DEFT |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
223 | PAY | AP processing lifecycle - Payments | PAY-223 | Functionality | NO | BAU | Oracle | Run payment batch for : Electronic / Standard |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
224 | PAY | AP processing lifecycle - Payments | PAY-224 | Functionality | NO | BAU | Oracle | Run payment batch for : Employee |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
225 | PAY | AP processing lifecycle - Payments | PAY-225 | Functionality | NO | BAU | Oracle | Run payment batch for : USD Cheque / SPH |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
226 | PAY | AP processing lifecycle - Payments | PAY-226 | Functionality | NO | BAU | Oracle | Run payment batch for : USD Cheque / Standard |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
227 | PAY | AP processing lifecycle - Payments | PAY-227 | Functionality | NO | BAU | Oracle | CTX Payment |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
228 | PAY | AP processing lifecycle - Payments | PAY-228 | Functionality | NO | BAU | Oracle | A2P Payment |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
229 | PAY | AP processing lifecycle - Payments | PAY-229 | Functionality | NO | BAU | Oracle | Run Unaccounted report |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
230 | PAY | AP processing lifecycle - Payments | PAY-230 | Functionality | NO | BAU | Oracle | Run view accounting lines for specific cost centre / gl |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
231 | PAY | AP processing lifecycle - Payments | PAY-231 | Functionality | NO | BAU | Oracle | Update bank account information at invoice level |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
232 | PAY | AP processing lifecycle - Payments | PAY-232 | Functionality | NO | BAU | Oracle | Validate invoice individually |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
233 | PAY | AP processing lifecycle - Payments | PAY-233 | Functionality | NO | BAU | Oracle | View accounting lines on individual invoices |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
234 | PAY | AP processing lifecycle - Payments | PAY-234 | Functionality | NO | BAU | Oracle | Void 1: Cancel payment and reissue |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
235 | PAY | AP processing lifecycle - Payments | PAY-235 | Functionality | NO | BAU | Oracle | Amending schedule payment date to release an holdback amount. |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
236 | PAY | AP processing lifecycle - Payments | PAY-236 | Functionality | NO | BAU | Oracle | Foreign supplier, currency other then USD or Cad (ONLY IN BMO CAD) |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
237 | PAY | AP processing lifecycle - Payments | PAY-237 | Functionality | NO | BAU | Oracle | To change Payment terms |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
238 | PAY | AP processing lifecycle - Payments | PAY-238 | Functionality | NO | BAU | Oracle | Wrong currency |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
239 | PAY | AP processing lifecycle - Payments | PAY-239 | Functionality | NO | BAU | Oracle | Run an ICE file (added DMC 08/20/20) |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
240 | PAY | AP processing lifecycle - Payments | PAY-240 | Functionality | NO | BAU | Oracle | Do tax adjustment (added DMC 08/20/2020) |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
241 | PAY | AP processing lifecycle - Payments | PAY-241 | Functionality | NO | BAU | Oracle | Run Payables Approval Process (added DMC 08/20/20) |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
242 | PAY | AP processing lifecycle - Payments | PAY-242 | Functionality | NO | BAU | Oracle | Run Payables Approval Process (added DMC 08/20/20) - BLOTTER |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
243 | PAY | AP processing lifecycle - Payments | PAY-243 | Functionality | NO | BAU | Oracle | Run Create Accounting (added DMC 08/20/20) - BLOTTER |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
244 | PAY | AP processing lifecycle - Payments | PAY-244 | Functionality | NO | BAU | Oracle | Run Published Actual Payments (added DMC 08/20/20 |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
245 | PAY | AP processing lifecycle - Payments | PAY-245 | Functionality | NO | BAU | Oracle | Run Payment Register Report (added DMC 08/20/20 |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
246 | PAY | AP processing lifecycle - Payments | PAY-246 | Functionality | NO | BAU | Oracle | Run HAR GLM Extract from AP |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
247 | PAY | AP processing lifecycle - Payments | PAY-247 | Functionality | NO | BAU | Oracle | Run HAR GLM Extract from FA |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
248 | PAY | AP processing lifecycle - Payments | PAY-248 | Functionality | NO | BAU | Oracle | Run HAR IBUK Extract from AP |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
249 | PAY | AP processing lifecycle - Payments | PAY-249 | Functionality | NO | BAU | Oracle | Run HNC CODA Extract from AP (added DMC 08/20/20) |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
250 | PAY | AP processing lifecycle - Payments | PAY-250 | Functionality | NO | BAU | Oracle | Void Report |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
251 | PAY | AP processing lifecycle - Payments | PAY-251 | Functionality | NO | BAU | Oracle | Run BMO ICLEAR File - Job |  |  |  | Mary-Ann | Tiffany Sadler | Payments | TO TEST |  |  | BMO Harris N.A.
252 | Recon | AP processing lifecycle-Recon | Recon-252 | Functionality | NO | BAU | Oracle | Run daily BMO & NB AP Liability TB reports |  |  |  | Raymond Gourgi | Raymond Gourgi | Fin Govn | TO TEST |  |  | BMO Harris N.A.
253 | Recon | AP processing lifecycle-Recon | Recon-253 | Functionality | NO | BAU | Oracle | Run bmo account analysis report |  |  |  | Raymond Gourgi | Raymond Gourgi | Fin Govn | TO TEST |  |  | BMO Harris N.A.
254 | Recon | AP processing lifecycle-Recon | Recon-254 | Functionality | NO | BAU | Oracle | Run void payment register |  |  |  | Raymond Gourgi | Raymond Gourgi | Fin Govn | TO TEST |  |  | BMO Harris N.A.
255 | Recon | AP processing lifecycle-Recon | Recon-255 | Functionality | NO | BAU | Oracle | Run payment register |  |  |  | Raymond Gourgi | Raymond Gourgi | Fin Govn | TO TEST |  |  | BMO Harris N.A.
256 | Recon | AP processing lifecycle-Recon | Recon-256 | Functionality | NO | BAU | Oracle | Run monthly BMO & NB AP Liability TB reports |  |  |  | Raymond Gourgi | Raymond Gourgi | Fin Govn | TO TEST |  |  | BMO Harris N.A.
257 | Recon | AP processing lifecycle-Recon | Recon-257 | Functionality | NO | BAU | Oracle | Run monthly reports for BMO FA (unposted mass addition, cost summary, reserve summary, reserve summary (accum.), CIP summary, asset retirement, asset retirement (accum.)) |  |  |  | Raymond Gourgi | Raymond Gourgi | Fin Govn | TO TEST |  |  | BMO Harris N.A.
258 | Recon | AP processing lifecycle-Recon | Recon-258 | Functionality | NO | BAU | Oracle | Run monthly reports for Harris (cost, reserve, CIP, unposted) |  |  |  | Raymond Gourgi | Raymond Gourgi | Fin Govn | TO TEST |  |  | BMO Harris N.A.
259 | Recon | AP processing lifecycle-Recon | Recon-259 | Functionality | NO | BAU | Oracle | Run monthly reports for Harris Tax (account analysis rpt) |  |  |  | Raymond Gourgi | Raymond Gourgi | Fin Govn | TO TEST |  |  | BMO Harris N.A.
260 | Recon | AP processing lifecycle-Recon | Recon-260 | Functionality | NO | BAU | Oracle | Run On hold reports (OIL) for all entities |  |  |  | Raymond Gourgi | Raymond Gourgi | Fin Govn | TO TEST |  |  | BMO Harris N.A.
261 | Recon | AP processing lifecycle-Recon | Recon-261 | Functionality | NO | BAU | Oracle | View payments & invoices (distribution, history..) |  |  |  | Raymond Gourgi | Raymond Gourgi | Fin Govn | TO TEST |  |  | BMO Harris N.A.
262 | Recon | AP processing lifecycle-Recon | Recon-262 | Functionality | NO | BAU | Oracle | Withholding Tax by supplier report |  |  |  | Raymond Gourgi | Raymond Gourgi | Fin Govn | TO TEST |  |  | BMO Harris N.A.
263 | PO/FA-E2E | FA processing lifecycle | PO/FA-E2E-263 | E2E | YES | LENC,CC,SUBS, LOC,TAX | Coupa-IDP-Oracle | E2E FA - PO to INV to FA flow | create requisition from Catalog as per 'Test Details' column | Requisition #1067824 PO #31069629 Issued | invoice appeared in Oracle | David Stein / Sri Sinnathurai / Dyanne Tully | Martin/Tiffany/Natalie | FA | TO TEST | End User, |  | BMO Harris N.A.
264 | PO/FA-E2E | FA processing lifecycle | PO/FA-E2E-264 | E2E | YES | LENC,CC,SUBS, LOC,TAX | Coupa-IDP-Oracle | E2E FA - PO to INV to FA flow | create requisition from Catalog as per 'Test Details' column | Requisition #1067825 PO #51069630 Issued | invoice appeared in Oracle | David Stein / Sri Sinnathurai / Dyanne Tully | Martin/Tiffany/Natalie | FA | TO TEST |  |  | BMO Harris N.A.
265 | PO/FA-E2E | FA processing lifecycle | PO/FA-E2E-265 | E2E | YES | LENC,CC,SUBS, LOC,TAX | Coupa-IDP-Oracle | E2E FA - PO to INV to FA flow | create requisition from Catalog as per 'Test Details' column | Requisition #1067826 PO #71069631 Issued | invoice appeared in Oracle | David Stein / Sri Sinnathurai / Dyanne Tully | Martin/Tiffany/Natalie | FA | TO TEST |  |  | BMO Harris N.A.
266 | PO/FA-E2E | FA processing lifecycle | PO/FA-E2E-266 | E2E | YES | LENC,CC,SUBS, LOC,TAX | Coupa-IDP-Oracle | E2E FA - PO to INV to FA flow | create requisition from Catalog as per 'Test Details' column | Requisition #1067827 PO #91069632 Issued | invoice appeared in Oracle | David Stein / Sri Sinnathurai / Dyanne Tully | Martin/Tiffany/Natalie | FA | TO TEST |  |  | BMO Harris N.A.
267 | INV/FA-E2E | FA processing lifecycle | INV/FA-E2E-267 | E2E | YES | LENC,CC,SUBS, LOC,TAX | Coupa-IDP-Oracle | E2E FA - NON-PO Invoice | create requisition from Catalog as per 'Test Details' column | NON-PO for CRE invoices Invoice #5429 - DELMEADE CONSTRUCTION LTD |  | David Stein / Dyanne Tully | Tiffany / Natalie | FA/AP | TO TEST |  |  | BMO Harris N.A.
268 | INV/FA-E2E | FA processing lifecycle | INV/FA-E2E-268 | E2E | YES | LENC,CC,SUBS, LOC,TAX | Coupa-IDP-Oracle | E2E FA - NON-PO Invoice | create requisition from Catalog as per 'Test Details' column | NON-PO for CRE invoices BGIS GLOBAL INTEGRATED SOLUTIONS Invoice #PD0920-2065622_QC_E |  | David Stein / Dyanne Tully | Tiffany / Natalie | FA/AP | TO TEST |  |  | BMO Harris N.A.
269 | INV/FA-E2E | FA processing lifecycle | INV/FA-E2E-269 | E2E | YES | LENC,CC,SUBS, LOC,TAX | Coupa-IDP-Oracle | E2E FA - Prepaid Invoice | PREPAID INVOICE | INVOICE # 2020-815 GREATER MILWAUKEE COMMITTEE |  | David Stein /Dyanne Tully | Tiffany / Natalie | FA/AP | TO TEST |  |  | BMO Harris N.A.
270 | FA | FA processing lifecycle | FA-270 | Functionality | NO | BAU | Oracle | Change Terms | Change Terms | Change Term from 10 yrs to 15 yrs and do an unplanned depreciationgoing forward |  | David Stein /Dyanne Tully | Tiffany / Natalie | FA | TO TEST |  |  | BMO Harris N.A.
271 | FA | FA processing lifecycle | FA-271 | Functionality | NO | BAU | Oracle | Create manual asset 1CIP + 1 CAP | Create manual asset 1CIP + 1 CAP | Project Name : BUS: Emerging Payments Program Project # PR017320 FI#: FI014020 Assignment: 00055.D7503.211132.000 Amount: 2,350CAD Project Name : AML Robotics Carry Over and Maintenance - Tech Project # PR025164 Funding Item ID: FI#008183 Assignment: 00055. H8090.2111000.000 Amount : 2,632.00CAD |  | David Stein | Natalie Vrkic | FA | TO TEST |  |  | BMO Harris N.A.
272 | FA | FA processing lifecycle | FA-272 | Functionality | NO | BAU | Oracle | Capitalizing assets | Capitalizing assets | Assets should move from CIP to CAP |  | David Stein | Natalie Vrkic | FA | TO TEST |  |  | BMO Harris N.A.
273 | FA | FA processing lifecycle | FA-273 | Functionality | NO | BAU | Oracle | Assets retirement | Assets retirement | Write off |  | David Stein | Natalie Vrkic | FA | TO TEST |  |  | BMO Harris N.A.
274 | FA | FA processing lifecycle | FA-274 | Functionality | NO | BAU | Oracle | Create Manual Asset | Create Manual Asset | Create manual asset for a Cap Purchase from BMO Foreign Office (e.g Taipei) |  | David Stein | Natalie Vrkic | FA | TO TEST |  |  | BMO Harris N.A.
275 | FA | FA processing lifecycle | FA-275 | Functionality | NO | BAU | Oracle | Create a manual assets | Create a manual assets | 1 Capitalized asset . |  | David Stein | Natalie Vrkic | FA | TO TEST |  |  | BMO Harris N.A.
276 | FA | FA processing lifecycle | FA-276 | Functionality | NO | BAU | Oracle | Adjust an asset manually | Adjust an asset manually | Retire A#388736 |  | David Stein | Natalie Vrkic | FA | TO TEST |  |  | BMO Harris N.A.
277 | FA | FA processing lifecycle | FA-277 | Functionality | NO | BAU | Oracle | Change cost center | Change cost center | Change CC for a# 385240 |  | David Stein | Natalie Vrkic | FA | TO TEST |  |  | BMO Harris N.A.
278 | FA | FA processing lifecycle | FA-278 | Functionality | NO | BAU | Oracle | Change cost center | Change cost center | 1 asset Going forward and 1 asset backdated |  | David Stein | Natalie Vrkic | FA | TO TEST |  |  | BMO Harris N.A.
279 | FA | FA processing lifecycle | FA-279 | Functionality | NO | BAU | Oracle | Change the category of an asset | Change the category of an asset | 1 asset Going forward and 1 asset backdated including unplanned depreciation |  | David Stein | Natalie Vrkic | FA | TO TEST |  |  | BMO Harris N.A.
280 | FA | FA processing lifecycle | FA-280 | Functionality | NO | BAU | Oracle | Write-off and sale assets | Write-off and sale assets | Need to test write off effective for current period and back dated. Also do a few with the Sales fonction |  | David Stein | Natalie Vrkic | FA | TO TEST |  |  | BMO Harris N.A.
281 | FA | FA processing lifecycle | FA-281 | Functionality | NO | BAU | Oracle | Create a manual assets | Create a manual assets | 1 CIP and 1 Capital |  | David Stein | Natalie Vrkic | FA | TO TEST |  |  | BMO Harris N.A.
282 | FA | FA processing lifecycle | FA-282 | Functionality | NO | BAU | Oracle | Adjust an asset manually | Adjust an asset manually | 1 CIP and 1 Capital. Try to apply a credit to an assset or bring it to zero |  | David Stein | Natalie Vrkic | FA | TO TEST |  |  | BMO Harris N.A.
283 | FA | FA processing lifecycle | FA-283 | Functionality | NO | BAU | Oracle | run the daily recon report | run the daily recon report | Mass addition create BMO FA Information update Mass addition create report Mass addition delete report Mass addition status report Mass addition Posting report Unposted report Create accounting Cost clearing Report |  | David Stein | Natalie Vrkic | FA | TO TEST |  |  | BMO Harris N.A.
284 | FA | FA processing lifecycle | FA-284 | Functionality | NO | BAU | Oracle | Capitalize CIP Asset | Capitalize CIP Asset |  |  | David Stein | Natalie Vrkic | FA | TO TEST |  |  | BMO Harris N.A.
285 | FA | FA processing lifecycle | FA-285 | Functionality | NO | BAU | Oracle | DEP RUN | DEP RUN |  |  | David Stein | Natalie Vrkic | FA | TO TEST |  |  | BMO Harris N.A.
286 | FA | FA processing lifecycle | FA-286 | Functionality | NO | BAU | Oracle | run the daily recon report | run the daily recon report | Mass addition create BMO FA Information update Mass addition create report Mass addition delete report Mass addition status report Mass addition Posting report Unposted report Create accounting Cost clearing Report |  | David Stein | Natalie Vrkic | FA | TO TEST |  |  | BMO Harris N.A.
287 | FA | FA processing lifecycle | FA-287 | Functionality | NO | BAU | Oracle | Change CC and category | Change CC and category | ref to A#1300125/1300124 - for BMOA Refer to asset # 1000091 change CC to H8090 and 1000092 change Category from CPTR to CH5y for BMO CAN CAD Refer Asset # 455079 Change CC to D6585 and 378021 from LITP to Fur |  | David Stein | Natalie Vrkic | FA | TO TEST |  |  | BMO Harris N.A.
288 | FA | FA processing lifecycle | FA-288 | Functionality | NO | BAU | Oracle | Change date in serviceand amortise adj going forward | Change date in serviceand amortise adj going forward | Refer to A#1000073 and 1000074 for BMO CAN CAD . |  | David Stein | Natalie Vrkic | FA | TO TEST |  |  | BMO Harris N.A.
289 | FA | FA processing lifecycle | FA-289 | Functionality | NO | BAU | Oracle | Run gain and Loss and asset retirement report | Run gain and Loss and asset retirement report |  |  | David Stein | Natalie Vrkic | FA | TO TEST |  |  | BMO Harris N.A.
290 | HOR | Lease administration processes | HOR-290 | Functionality | YES | LENC, ADDR/LOC, User | Horizon | Ask Wanda/Vikram |  |  |  | Ciciora, Wanda | Tiffany Sadler |  | TO TEST
291 | HOR | Lease administration processes | HOR-291 | Functionality | YES | LENC, ADDR/LOC, User | Horizon | Ask Wanda/Vikram |  |  |  | Ciciora, Wanda | Tiffany Sadler |  | TO TEST
292 | HOR | Lease administration processes | HOR-292 | Functionality | YES | LENC, ADDR/LOC, User | Horizon | Ask Wanda/Vikram |  |  |  | Ciciora, Wanda | Tiffany Sadler |  | TO TEST
293 | HOR | Lease administration processes | HOR-293 | Functionality | YES | LENC, ADDR/LOC, User | Horizon | Ask Wanda/Vikram |  |  |  | Ciciora, Wanda | Tiffany Sadler |  | TO TEST
294 | EL | External labor hiring lifecycle | EL-294 | Functionality | YES | LENC, ADDR/LOC, User | Beeline | Ask Richard/Taruneet |  |  |  | Richard Wiskin | Richard Wiskin |  | TO TEST
295 | EL | External labor hiring lifecycle | EL-295 | Functionality | YES | LENC, ADDR/LOC, User | Beeline | Ask Richard/Taruneet |  |  |  | Richard Wiskin | Richard Wiskin |  | TO TEST
296 | EL | External labor hiring lifecycle | EL-296 | Functionality | YES | LENC, ADDR/LOC, User | Beeline | Ask Richard/Taruneet |  |  |  | Richard Wiskin | Richard Wiskin |  | TO TEST
297 | EL | External labor hiring lifecycle | EL-297 | Functionality | YES | LENC, ADDR/LOC, User | Beeline | Ask Richard/Taruneet |  |  |  | Richard Wiskin | Richard Wiskin |  | TO TEST
298 | EL | External labor hiring lifecycle | EL-298 | Functionality | YES | LENC, ADDR/LOC, User | Beeline | Ask Richard/Taruneet |  |  |  | Richard Wiskin | Richard Wiskin |  | TO TEST
299 | EL | External labor hiring lifecycle | EL-299 | Functionality | YES | LENC, ADDR/LOC, User | Beeline | Ask Richard/Taruneet |  |  |  | Richard Wiskin | Richard Wiskin |  | TO TEST
300 | EL | External labor hiring lifecycle | EL-300 | Functionality | YES | LENC, ADDR/LOC, User | Beeline | Ask Richard/Taruneet |  |  |  | Richard Wiskin | Richard Wiskin |  | TO TEST
301 | EL | External labor hiring lifecycle | EL-301 | Functionality | YES | LENC, ADDR/LOC, User | Beeline | Ask Richard/Taruneet |  |  |  | Richard Wiskin | Richard Wiskin |  | TO TEST
302 | EL | External labor hiring lifecycle | EL-302 | Functionality | YES | LENC, ADDR/LOC, User | Beeline | Ask Richard/Taruneet |  |  |  | Richard Wiskin | Richard Wiskin |  | TO TEST
303 | EL | External labor hiring lifecycle | EL-303 | Functionality | YES | LENC, ADDR/LOC, User | Beeline | Ask Richard/Taruneet |  |  |  | Richard Wiskin | Richard Wiskin |  | TO TEST
304 | DA-E2E | Reporting | DA-E2E-304 | E2E | YES | LENC,SUBS/PG, CC, CG, ADDR/LOC, Users, TAX | Spotfire/BI | Ask Tyler/Stephen |  |  |  | Lindzi/Jonathan | Tyler/Stephen |  | TO TEST
305 | PCC - UI | UI/UX & User Other | PCC - UI-305 | UX | YES | LENC,SUBS/PG, CC, CG, ADDR/LOC, Users, TAX | Coupa | UI changes not reported in release notes | Expense Tab-Expense Reports | Searching for expense reports using Expense Reports category under Expenses Tab |  | Chantal ElAzzi | Dan Muldoon | PCC | TO TEST |  |  | BMO Harris N.A.
306 | INTEGR | Integration/Automation Specific | INTEGR-306 | E2E | YES | LENC,SUBS/PG, CC, CG, ADDR/LOC, Users, TAX, Downstream | Oracle |  |  |  |  | Poorni | Rondrigo |  | TO TEST
307 | INTEGR | Integration/Automation Specific | INTEGR-307 | E2E | YES | LENC,SUBS/PG, CC, CG, ADDR/LOC, Users, TAX, Downstream | Oracle |  |  |  |  | Poorni | Rondrigo |  | TO TEST
308 | INTEGR | Integration/Automation Specific | INTEGR-308 | E2E | YES | LENC,SUBS/PG, CC, CG, ADDR/LOC, Users, TAX, Downstream | Coupa |  |  |  |  | Poorni | Rondrigo |  | TO TEST
309 | INTEGR | Integration/Automation Specific | INTEGR-309 | E2E | YES | LENC,SUBS/PG, CC, CG, ADDR/LOC, Users, TAX, Downstream | Beeline |  |  |  |  | Poorni | Rondrigo |  | TO TEST
310 | INTEGR | Integration/Automation Specific | INTEGR-310 | E2E | YES | LENC,SUBS/PG, CC, CG, ADDR/LOC, Users, TAX, Downstream | Horizon |  |  |  |  | Poorni | Rondrigo |  | TO TEST
311 | INTEGR | Integration/Automation Specific | INTEGR-311 | E2E | YES | LENC,SUBS/PG, CC, CG, ADDR/LOC, Users, TAX, Downstream | SEMS |  |  |  |  | Poorni | Rondrigo |  | TO TEST
312 | Other | ServiceNow | Other-312 | Functionality | YES | LENC | ServiceNow |  |  |  |  | TBD | David Ho |  | TO TEST
313 | Other | ServiceNow | Other-313 | Functionality | YES | LENC | ServiceNow |  |  |  |  | TBD | David Ho |  | TO TEST
314 | Other | External Testers TDEV |  |  | YES | LENC | Coupa |  |  |  |  | TBD | David Ho
315 | NEW Punch-Out |  |  | E2E | YES | TS/PO/PT | Coupa-Oracle
316 | NEW Punch-Out |  |  | E2E | YES | TS/PO/PT | Coupa-Oracle
317 | New Trusted |  |  | E2E | YES | TS/PO/PT
318 | New Trusted |  |  | E2E | YES | TS/PO/PT
319 | New Trusted |  |  | E2E | YES | TS/PO/PT